## Slide 1: Business Process Review Project Charter

## Slide 2: Project Charter Cover Page
Example
Project Title | Reduce Delivery Errors of CHL Package Delivery Process |  |  | 
Project Sponsor | Bruce Backer |  |  | 
Project Leader | Mark Leader |  |  | 
Team Members | Sara Speed, Ronny Run (Logistics), Richard Rush (Director, Logistics) |  |  | 
Budget Support | Penny Pence (Accounting) |  |  | 
Project Status Start: 7 July | Phase | Planned | Actual | Status
 | Define | 7 July | 7 July | Done
 | Measure | 27 Aug |  | In Progress
 | Analyze | 18 Sep |  | In Progress
 | Improve | 08 Oct |  | 
 | Control | Ongoing |  | 

## Slide 3: Project Charter Problem and Objective
Example
Case for Change | Customer Satisfaction for Package Delivery is very low leading to non-renewal of contracts as well as customers’ attrition. | 
Problem Statement | Customer Dissatisfaction is driven by long delivery time, wrong packaging and delivery to wrong locations. | 
Project Objective | Reducing delivery errors including call by customer to delivery from currently 35.5% to 0% by end of June. | 
Project Scope | Start: | Customer calls and demands delivery service
 | End: | Customer receives package
 | Included: | All logistics steps
 | Excluded: | Pricing and Invoicing

## Slide 4: Project Charter Progress Monitoring
Example
Primary Indicators | Indicators |  | Baseline | Ideal | Goal
 | Y1: % on time delivery |  | 25.0% | 100.0% | 100.0%
 | Y2: % correct location |  | 85.0% | 100.0% | 100.0%
 | Y3: % correct packaging |  | 83.3% | 100.0% | 100.0%
Overall Outcome and Benefits | Customers receive package on time and correct, i.e., they can serve their customers with excellent quality. |  |  |  | 
Financial Savings (if any) | SGD 30k | Additional business due to customer satisfaction and loyalty. |  |  | 
Notes: Total approved cases after appeal / total rejected cases.
Take away for this slide
When we try to improve the cycle time for the appeal process, we should not have any defect for outcome of appeal case.
40% rejected cases from application population (S Pass)
Why are we looking at the appeals which are approved subsequently?-Because these might be reasons why people are keen on appealing. If the chance of a successful appeal is low, then applicant/employer might not find appealing worthwhile. To cut down these successful appeals, we might also want to reduce the no. of cases where it will definitely be approved upon rejection, eg. Levy default, insufficient quota at pt of application.